## Sheet1
Week# | Milestone | Tasks | Notes
1 | R&D
ML High Level Understandings
Problem Research
Dataset Research
2 | Finalised Dataset
Exploring Dataset
Filtering Dataset
Annotating Dataset
Initial Model for Classification
Constructing our first Model for Symbol Classification
Model Evaluation
3 | Yolo Object Detection model for Care symbol Localisation
Baseline Classification Model
Consrtucting Baseline Model - Training - Testing - Evaluating
Model Hyper Parameter Tuning
Model Experimenation
4 | Classification & Detection Model Development Cycles
Model Developments
Model Training & Testing
Model Preformance Evaluation And Comparision
OCR on Label Texts